## Action Items
3. Action Items
Last updated: 24 March 2026
🔴 High Priority
Task | Owner | Status | Notes
Await Shanti’s response re: timeline and hosting | Shanti | ⏳ Waiting | Email sent 24 March. Holding payment until confirmed. Do not pay until clarity received.
Confirm Shanti will set up Bookscan/Shopify connector | Shanti | ⏳ Waiting | He confirmed competitor has it — need confirmation he’ll do ours and when
Confirm Shanti will keep WordPress live during migration | Shanti | ⏳ Waiting | Critical — cannot go dark during Shopify build
Book Bookscan/Shopify demo with Shanti | Lance + Louisa | ⏳ Waiting | Requested in email — needed before build starts
Confirm Louisa’s email for Shopify user account | Lance | ⏳ Pending | Check with Louisa whether to use books@bmbooks.co.nz or set up a personal email (e.g. louisa@bmbooks.co.nz or personal Gmail). Once confirmed, add her as staff in Shopify → Settings → Users and transfer store ownership to her.
Set up Louisa’s personal email / Google account | Louisa | ⏳ Needed | Required for: GA access, Search Console, Cloudflare transfer, Shopify ownership. Suggest louisa@bmbooks.co.nz or personal Gmail. Currently using shared books@bmbooks.co.nz for everything.
Move UpdraftPlus backup to Louisa’s Google Drive | Lance | ⏳ Waiting | Waiting on Louisa’s Google account details
Transfer Cloudflare account to Louisa | Lance | ⏳ Pending | Do after Google account confirmed
Confirm + delete 27GB backup file on server | Shanti | ✅ Done | Deleted from cPanel 24 March 2026
🟠 Medium Priority
Task | Owner | Status | Notes
Shopify migration | Lance + Louisa | 🔄 In Progress | Store created. Settings, shipping, policies, customer accounts done. Horizon theme installed — stopped at Colors step. Brand colour: #430451. Resume theme setup next session. Bookscan connector pending Shanti.
Complete Imagify WebP optimisation | Auto | ⏸ Paused | Deactivated 24 March — was causing CPU 110% spike and 503 errors. Do not reactivate. Resolves on Shopify.
Monitor file usage (inode limit) | Lance | ⚠️ Watch | At 549,060 / 600,000 (91.5%). lscache already 513MB and growing. Do not install anything that generates files. Check weekly. If approaching 600k, purge LiteSpeed cache via LiteSpeed Cache → Manage → Purge All.
LiteSpeed Cache configuration | Lance | ⏸ Deferred | Core settings configured. Object Cache (Redis) and further tuning deferred — server too close to inode limit. Resume on Shopify.
SEO review and testing | Lance | ⏸ Deferred | All ~110 category descriptions + focus keyphrases added. robots.txt updated. Remaining issues (364 5xx errors, Core Web Vitals) will resolve on Shopify — no further WordPress SEO work planned.
Set up Shopify Payments | Louisa | ⏳ Pending | Needs Louisa's bank account number and IRD number. Replaces WooPayments (credit/debit, Apple Pay, Google Pay).
Audit WooCommerce webhooks and integrations | Lance | ⏳ Pending | Check WooCommerce → Settings → Advanced → Webhooks for anything Shanti configured. Also check WooCommerce → Settings → Integration tab. Identify anything that needs to be replicated or decommissioned on Shopify before go-live.
Verify store details with Louisa | Lance | ⏳ Pending | Confirm: selling countries list, store phone number, whether to enable free shipping over $100 (currently disabled on WordPress). Verify with accountant: taxes set to "Not collecting" across all regions — books are GST zero-rated in NZ but confirm this is correct treatment for all markets. Get business registration number and GST number for Terms of Service Section 25.
Set up Google login for customer accounts | Lance | ⏳ Blocked | Requires Google Cloud Console project setup. Needs Louisa’s Google account. Instructions saved in Shopify → Settings → Customer accounts → Google.
Connect Google Analytics | Lance | ⏳ Blocked | Need Louisa’s Google account first
Non-branded keywords | ⏳ Pending | Biggest growth opportunity — defer until after migration
🟢 Strategic
Task | Owner | Status | Notes
Contact Abbey (Black Sheep Design) re: original design assets | Lance | ⏳ Pending | Louisa paid Abbey to design the current website. Request original brand files — colours, fonts, logos, any design assets — to replicate on Shopify theme. Email: TBC
Build Figma design guidelines | Lance | ⏳ Pending | Defer until Shopify theme selected
Competitive landscape deep dive | Lance | ⏳ Pending | Manual review of Hedley’s, Bookhero, Unity Books

## Roadmap
2. Roadmap
Format: Now / Next / Later
North Star: Conversion Rate (Product View → Purchase Completion)
🔵 Now (March–May 2026)
Focus: Shopify migration + stabilise current site while transitioning
Initiative | Status | Why It Matters
Shopify Migration | 🔄 In Progress | Store created. Settings, shipping, policies done. Theme in progress. Bookscan connector pending Shanti.
Hosting Performance (LiteSpeed Cache) | 🔄 In Progress | LCP 9.9s on mobile — cache installed, configuration in progress
Disk Cleanup + Server Health | ✅ Done | Server at capacity causing 503 errors
SEO Foundation + Google Indexing | ✅ Done | All 110 categories updated, 404s fixed, robots.txt updated
Backup Strategy | ✅ Done | No safe recovery path existed
Imagify WebP Conversion | ⏸ Paused | Deactivated — caused CPU 110% spike. Resolves on Shopify.
Hosting Ownership (move to Louisa) | ⏳ Pending | Resolves via Shopify migration
🟡 Next (Q2 2026 — on Shopify)
Focus: Get Shopify store live and optimised
Initiative | Why It Matters | Notes
Shopify theme setup + collections | Site needs to be functional before launch | Mirror current category structure
Bookscan connector live on Shopify | 40,000 products depend on it | Shanti to set up
Domain transfer to Shopify | Cut over from WordPress | Coordinate with Abbey (Black Sheep Design)
SEO migration (meta, descriptions, structure) | Preserve search rankings built on WordPress | Category descriptions ready to port
Google Analytics + Search Console setup | No visibility without it | Needs Louisa's Google account
Payment gateway setup | Can't trade without it | Shopify Payments or existing gateway
Non-branded SEO (NZ bookstore keywords) | 92% of traffic is branded | Resume after migration stable
🟣 Later (Q3–Q4 2026)
Focus: Drive growth on Shopify
Initiative | Why It Matters
Full Product Inventory Audit | 20% refund rate — customers buying unavailable books
Checkout Flow Optimisation | Reduce drop-off at final purchase step
My Account Experience | Improve loyalty and repeat purchases
Marketing Automation | Email + cart abandonment recovery
Brand Refresh | Website + social consistency
Google Merchant / Shopping | 17.72% CTR — best performing channel

## Future State
6. Future State & Strategy
*Where we want to be and how we get there*
🎯 Vision
A fast, reliable, fully Louisa-owned website with no vendor dependency — running on a platform that matches or exceeds the competitive set.
🔄 Current State vs Future State
Now | Future
Platform | WordPress + WooCommerce | Shopify
Hosting | A2 via Shanti (reseller) | Shopify (Louisa’s account)
Domain Control | Black Sheep Design | Louisa direct (via SiteName)
Backups | Lance’s Google Drive | Louisa’s Google Drive
CDN | Cloudflare (Lance’s account) | Shopify CDN built-in
TTFB | 4.8s (mobile) | <0.5s
LCP | 9.9s (mobile) | <2.5s
Refund Rate | 20% | <5%
Monthly Orders | 42 | 100+
Shopify Migration Plan
Context
Shanti (CEO of Bookscan, also our hosting reseller) has pushed for migration end of week (March 2026). This is not realistic. We’ve requested 2 months and are awaiting confirmation. Key email sent 24 March — holding payment until his position is clarified.
Bookscan/Shopify connector is confirmed to exist (Shanti set it up for a competitor). Shanti will set up our connector. We’ve requested a demo.
✅ Benefits
• Louisa owns account directly — no vendor dependency on Shanti for hosting
• No hosting, plugins, or maintenance required
• Built-in CDN and performance (Hedley’s TTFB: ~0.44s)
• Predictable monthly cost
• Bookscan connector available and working
• Proven setup (used by Hedley’s Books)
🧾 Pre-Migration Checklist
• Await Shanti’s response re: timeline and payment
• Confirm Shanti will keep WordPress live during migration
• Get Bookscan/Shopify demo from Shanti
• Confirm Shanti will set up the connector and when
• Confirm Louisa’s Google account access
• Confirm domain transfer process with Abbey (Black Sheep Design)
• Set up Shopify account in Louisa’s name
🚀 Migration Steps
1. Set up Shopify account (Louisa’s name, email, payment)
2. Choose and configure Shopify theme
3. Rebuild collections (mirror current WooCommerce category structure — 110 categories documented)
4. Connect Bookscan via Shopify connector (Shanti to set up)
5. Port SEO content — category descriptions and meta data already written (file: /Users/lalfred/Documents/claude/BMBooks_Category_SEO.txt)
6. Set up payment gateway (Shopify Payments)
7. Migrate key pages (About, Contact, etc.)
8. Migrate customer accounts and order history
9. Set up Google Analytics and Search Console on new store
10. Full QA and testing before go-live
11. Ask Abbey to update nameservers (domain transfer)
12. Monitor rankings and traffic post-launch
13. Cancel Shanti hosting contract
📊 Summary
• Cost: $79–105 NZD/month (Shopify Basic–Shopify plan)
• Effort: High (2 months recommended)
• Risk: Low — Bookscan connector confirmed. Main risk is rushing the timeline.
• Annual saving vs WordPress: ~$733 NZD/year on Shopify Basic
See full cost breakdown → 13 Platform Cost Comparison
🗓 Timeline
Milestone | Target
Shanti confirms timeline and payment terms | ASAP
Bookscan/Shopify demo booked | ASAP
Shopify account created | Week 1
Theme selected and configured | Week 2
Bookscan connector live | Week 2–3 (Shanti dependency)
Collections and SEO content ported | Week 3–4
QA and testing | Week 5–6
Domain transfer and go-live | Week 7–8
WordPress hosting cancelled | After go-live confirmed stable

## Release Notes
9. Release Notes
*A running log of changes made to the website (most recent first)*
🚀 v1.2 — SEO Overhaul + Server Incident + Shopify Migration Decision
Date: 24 March 2026
Author: Lance Alfred
Summary
Full SEO audit and rebuild across all 110 product categories. Server incident caused by Imagify bulk optimisation consuming 110% CPU. Shopify migration decision made and documented. Platform cost comparison completed.
⚙️ Changes Made
SEO
• All ~110 WooCommerce product category descriptions written and added
• Focus keyphrases set for all categories
• Yoast SEO title template set to `%%term_title%% ¦ %%sitename%%` globally
• Top category pages manually submitted for reindexing in Google Search Console
• robots.txt updated to block junk search URLs (`/?s=`, `/?post_type=product&`, `/page/`)
• Redirection plugin installed — 301 redirect rule added for 906 deleted product 404s (later disabled — was catching live products, needs refinement)
• Category SEO content saved to: `/Users/lalfred/Documents/claude/BMBooks_Category_SEO.txt`
Performance
• LiteSpeed Cache installed and configured:
• Page cache, CSS/JS minification, lazy loading, browser cache enabled
• JS Combine left OFF (Divi compatibility)
• Font Display set to Swap
• Add Missing Sizes ON (fixes CLS)
• Imagify bulk optimisation deactivated — was causing CPU to hit 110% and memory to spike to 1GB, triggering 503 errors
Server Incident (24 March 20:00–21:00 NZST)
• Imagify bulk optimisation triggered CPU spike to 110%, memory to 1,001MB, IO to 2.07MB/s
• 286 memory faults, 124 IOPS faults recorded
• Site throwing 503 errors to customers during this period
• Resolution: Imagify deactivated. CPU returned to ~40%.
• File usage identified at 91.5% (549,060 / 600,000 inodes) — monitoring required
Shopify Migration
• Decision made to migrate to Shopify
• Bookscan/Shopify connector confirmed to exist (Shanti set up for competitor)
• Email sent to Shanti requesting 2 months timeline and clarification on hosting continuity
• Platform cost comparison completed — Shopify Basic saves ~$733 NZD/year
• Full cost comparison documented in: 13 Platform Cost Comparison
Shopify Store Setup (24 March 2026)
• Shopify store created under books@bmbooks.co.nz
• Store details configured: NZD currency, Metric units, Auckland timezone, NZ store address
• Markets configured: New Zealand (primary), International
• Shipping zones configured:
• New Zealand: 5 rates — Collect In Store (free), North Island $7.99, South Island $10.99, Rural North $11.99, Rural South $15.99. Transit: 3–5 business days.
• International: Manual quote at $0.00 — Australia, Singapore, UK, USA, Rest of World
• Note: Free shipping over $100 currently disabled — confirm with Louisa before enabling
• Policies set up: Privacy Policy, Return Policy, Terms of Service (from Shopify templates, customised for BMBooks)
• Customer accounts: New customer accounts enabled with login links in storefront + order confirmation emails
• Marketing opt-in: Pre-checked opt-in enabled at checkout
• Horizon theme installed — theme editor opened, brand colour #430451 to apply at next session
• Louisa email draft sent re: Shopify account ownership, Google account, Shopify Payments, store verification
📊 Metrics (PageSpeed — Mobile — 24 March 2026)
Metric | Result | Status
LCP | 9.9s | Poor
FCP | 2.1s | Needs improvement
TTFB | 4.8s | Poor — root cause is no caching + shared server
CLS | 0.5 | Poor — image dimensions missing
TBT | 70ms | Good
Performance Score | 48/100 | Poor
⚠️ Known Issues
• TTFB 4.8s — server too slow for uncached requests. Resolves on Shopify.
• File usage at 91.5% — approaching inode limit. Do not reactivate Imagify until resolved or migrated.
• 364 server errors (5xx) still in Search Console — likely caused by recurring CPU spikes
• Core Web Vitals: 249 poor URLs — all LCP related
🚀 v1.1 — Performance & Infrastructure Overhaul
Date: March 22, 2026
Author: Lance Alfred
Summary
Major performance improvements addressing slow LCP (5.4s) and server instability.
LCP improved to 3.5s in lab tests within one session.
⚙️ Changes Made
Infrastructure
• Cloudflare CDN set up on free plan (nameservers updated by Abbey at Black Sheep Design)
• LiteSpeed Cache plugin installed and configured
• WooCommerce cache exclusions set (cart, checkout, my-account)
• HTTP/2, HTTP/3, 0-RTT, Early Hints, Speed Brain, Rocket Loader enabled via Cloudflare
• Cloudflare Fonts enabled (replaces need for Google Fonts self-hosting plugin)
Performance
• Cart fragments disabled (was blocking page render)
• LCP hero image preload added
• Imagify WebP conversion started (in progress)
Server Cleanup
• ~30GB freed (old backups, WP Staging folder)
• Server resources improved:
• RAM: 100% → 20%
• CPU: 97% → 26%
Backup
• UpdraftPlus configured with Google Drive remote storage
• Database, plugins, and themes successfully backed up
📊 Metrics
Metric | Before | After (lab)
LCP | 5.4s | 3.5s
FCP | 5.1s | 3.2s
TBT | — | 10ms
Performance Score | — | 76/100
🧱 v1.0 — Initial Setup
Date: Pre-March 2026
Author: Unknown (Shanti / Barcode Solutions)
Summary
Original WordPress + WooCommerce site hosted on A2 Hosting via Barcode Solutions reseller.

## Platform Cost
13. Platform Cost Comparison
WordPress vs Shopify
Prepared: 24 March 2026
Exchange rate used: 1 USD = 1.75 NZD (approx)
Current WordPress Costs
Item | USD/year | NZD/year | Renewal | Notes
Hosting (Shanti/A2) | — | $1,080 | Annual | Shared server, 4 clients
Bookscan | — | $1,800 | Annual | Product catalog sync — 40,000 products
Imagify | $143.88 | $252 | 21 Apr 2026 | $11.99/month — image optimisation
Divi theme | $67 | $117 | 5 Dec 2026 | Page builder / theme
FiboSearch | $59 | $103 | 14 Mar 2027 | Advanced search plugin
WooCommerce | Free | Free | — | Core ecommerce plugin
Yoast SEO | Free | Free | — | SEO plugin
UpdraftPlus | Free | Free | — | Backup plugin
Cloudflare | Free | Free | — | CDN
Domain | TBC | TBD | Assumed same cost on both platforms — confirm with Abbey
**Total** | **$3,352 + domain**
Shopify Costs (Estimated)
Item | USD/year | NZD/year | Notes
Shopify Basic plan | $468 | ~$819 | $39 USD/month billed annually — suits current order volume (~42/month)
Bookscan connector | — | $1,800 | Same as now — assumed no additional fee for Shopify connector (TBD — confirm with Shanti)
Theme (Dawn) | Free | Free | Shopify's free theme — clean, fast, good starting point
Domain | TBC | TBD | Same cost as current — just pointed to Shopify, no new registration
SEO app | Free | Free | Shopify built-in SEO + Search & Discovery app
Cloudflare | Not needed | Free | Shopify has built-in global CDN
Backups | Not needed | Free | Shopify manages backups automatically
**Total** | **~$2,619 + domain**
If upgrading to Shopify plan (mid-tier)
Item | NZD/year | Notes
Shopify plan | ~$2,205 | Better reporting, lower transaction fees
All other items | Same as above
**Total** | **~$4,005 + domain** | Only worth it if order volume grows significantly
What You Stop Paying For on Shopify
Item | NZD/year saved | Replaced by
Hosting (Shanti) | $1,080 | Included in Shopify subscription
Imagify | $252 | Shopify handles image optimisation automatically
Divi theme | $117 | Replaced by Shopify theme (free or one-off)
FiboSearch | $103 | Shopify built-in search (free)
**Total savings** | **$1,552/year**
Side-by-Side Summary
WordPress (current) | Shopify Basic
Annual platform cost | $3,352 + domain | ~$2,619 + domain
Bookscan | $1,800 | $1,800 (unchanged)
**Total** | **$3,352 + domain** | **~$2,619 + domain**
**Annual saving on Shopify** | **~$733/year**
Performance (LCP) | 9.9s mobile | <2.5s (Shopify CDN)
Maintenance burden | High (plugins, updates, hosting issues) | Low (Shopify manages everything)
Ownership | Shanti controls hosting + domain | Louisa owns account directly
Vendor dependency | High (Shanti controls hosting + Bookscan) | Bookscan only
One-Off Migration Costs
Item | Estimated Cost | Notes
Shopify theme (if paid) | ~$600 NZD one-off | Optional — Dawn is free
Migration time (Lance) | Internal cost | Estimated 2 months part-time
Bookscan connector setup | TBC | Ask Shanti if there's a setup fee
Outstanding Items
Item | Assumption | Status
Domain registration cost | Same cost on both platforms — no change | TBD — confirm with Abbey
Bookscan connector on Shopify | No additional fee — included in existing Bookscan contract | TBD — confirm with Shanti
Transaction fees | $0 if using Shopify Payments (available in NZ) | TBD
Recommendation
Shopify Basic saves approximately $733 NZD/year over the current WordPress setup, while also:
• Eliminating server performance issues (9.9s LCP → target <2.5s)
• Removing dependency on Shanti for hosting
• Reducing ongoing maintenance burden significantly
The migration is worth doing regardless of Shanti's timeline pressure.